## Sheet1
Scrum Master | Jack |  |  |  |  | Individual Capacity
[6 empty] | Team Members | Hours
| Interval | 9/22-9/26 (4 days) |  |  |  | Yoshiki | 10 | 15
| Team Capacity (Hrs) | 51 |  |  |  | Devin | 12 | 11
| Assigned time (Hrs) | 51 |  |  |  | Jack | 10 | 6
| Unassigned Time (Hrs) | 0 |  |  |  | Phong | 10 | 12
[6 empty] | Zarif | 9 | 9
53
Work Item | Task Breakdown | Assigned | Story Points (Hours) 1sp:1hr | Complexity | Start Date | Due Date (Internal) | Due Date (External) | Status | Comments
Product Proposal | Product Proposal Low-Medium Complexity Features | Jack | 6 | Medium | 2023-09-22 | 2023-09-24 | 2023-09-27 | In Progress | Waiting for feedback - edits in meantime
| Product Proposal High Complexity Features | Yoshiki | 8 | High | 2023-09-22 | 2023-09-24 | 2023-09-27 | In Progress | Waiting for feedback - edits in meantime
Environment Setup | Environment Setup | All | 8 | Low | 2023-09-22 | 2023-09-24 | 2023-09-25 | In Progress | Will Colaberate to help lower eachothers time
BRD | BRD Scope | Devin | 2 | Low | 2023-09-22 | 2023-09-26 | 2023-09-27 | Not Started | Our project proposal scope is close to BRD's
| BRD User Types | Yoshiki | 5 | Medium | 2023-09-22 | 2023-09-26 | 2023-09-27 | Not Started
| BRD Low Complexity Features, Functional and Non-Functional | Zarif | 4 | High | 2023-09-22 | 2023-09-26 | 2023-09-27 | In Progress
| BRD Medium Complexity Features, Functional and Non-Functional | Devin | 7 | High | 2023-09-22 | 2023-09-26 | 2023-09-27 | Not Started | Includes most of our features, most are phase 2 in general
| BRD High Complexity Features, Functional and Non-Functional | Phong | 8 | High | 2023-09-22 | 2023-09-26 | 2023-09-27 | Not Started | Includes most of our features, most are phase 2 in general
| BRD Glossary | Zarif | 3 | Low | 2023-09-22 | 2023-09-26 | 2023-09-27 | Not Started
Task Breakdown Comments
Product Proposal | Broke into two components - less than 15 hrs after talking again
BRD | Broke into gradeable components for responsability assignment