## Sheet1
Date | Names | What did you do? | What will you do? | Blocked? | Comments?
2023-10-02 | Yoshiki | Product Proposal - Implement Feedback 2 | BRD Phase 1 - 3 Features
| Phong | Product Proposal - Implement Feedback 5 | BRD Phase 1 - 3 Features
| Jack (SM) | On break | BRD Phase 1 - 3 Features |  | Collaberate on motivational quote -> get feedback -> expand to others
| Devin | On break | Non Features Requirements (User Types, Scope)
| Zarif | On break | Glossary |  | Adding defenitions
2023-10-03 | Yoshiki | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features
| Phong | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features
| Jack | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features |  | Focusing on getting draft of recomendation engine to prof
| Devin | BRD Phase 1 - 3 Features, Non Features | BRD Phase 1 - 3 Features, Non Features
| Zarif | Working on Glossary | Finish Glossary
2023-10-04 | Yoshiki | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features, trello board
| Phong | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features |  | WAGMI
| Jack | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features |  | Hopeful of new class colaboration of brd
| Devin | BRD Phase 1 - 3 Features, Non Features | BRD Phase 1 - 3 Features, Non Features |  | Need to parallely work on reasearching for project planning
| Zarif | Working on Glossary | Finish Glossary
2023-10-05 | Yoshiki | Wasn't able to work on trello | BRD Phase 1 - 3 Features, trello board |  | Use the LLI creation user stories as a template
| Phong | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features
| Jack | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features |  | focus on implementing LLI creation/managemnet, as rec engine/calendar relies on it
| Devin | Wasn't able to work | User stories for all features |  | reasearching for project planning
| Zarif | Finished Glossary | BRD Phase 1 - 3 Features |  | Helping out other team members due to poor sprint planning
2023-10-06 | Yoshiki | Trello board expansion | BRD Phase 1 - 3 Features |  | BDR Phase 1 - Make user stories for Geospatial Map and LLI Reminder
| Phong | Wasn't able to work | BRD Phase 1 - 3 Features
| Jack | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features |  | Phong handled LLI creation/ management, doing story 2 for rec engine
| Devin | Wasn't able to work | User stories for all features |  | reasearching for project planning
| Zarif | BRD Phase 1 - 3 Features | Continue BRD Phase 1 - 3 Features
2023-10-07 | Yoshiki
Phong
Jack
Devin
Zarif
2023-10-08 | Yoshiki
Phong
Jack
Devin
Zarif
2023-10-09 | Yoshiki | Worked on BRD features tasks | Work on feedback given by professor |  | fixing the user stories, format the table
| Phong | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features |  | quantify requierments
| Jack | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features
| Devin | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features, Non Features |  | researching for project planning (milestone 1)
| Zarif | Continue BRD Phase 1 - 3 Features | Continue BRD Phase 1 - 3 Features
2023-10-10 | Yoshiki | BRD Phase 1 Features | Continue BRD Phase 1 Features |  | FINISH BRD!
| Phong | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features |  | FINISH BRD!
| Jack | BRD Phase 1 - 3 Features | BRD Phase 1 - 3 Features |  | FINISH BRD!
| Devin | BRD Phase 1 - 3 Features, Non Features | BRD Phase 1 - 3 Features, Non Features |  | FINISH BRD!
| Zarif | Continue BRD Phase 1 - 3 Features | Continue BRD Phase 1 - 3 Features |  | FINISH BRD!
2023-10-11 | Yoshiki
Phong
Jack
Devin
Zarif