## Sheet1
Scrum Master | Jack |  |  |  |  | Individual Capacity |  |  | Days unavailable - as per member
[6 empty] | Team Members | Hours
| Interval | 9/30-10/11 (12 days) |  |  |  | Yoshiki | 20 |  | Saturday
| Team Capacity (Hrs) | 105 |  |  |  | Devin | 25 |  | Monday and Tuesday
| Assigned time (Hrs) | 87 |  |  |  | Jack | 20 |  | Saturday, Sunday
| Unassigned Time (Hrs) | 18 |  |  |  | Phong | 20 |  | Saturday and Sunday
[6 empty] | Zarif | 20 |  | Saturday and Sunday
Work Item | Task Breakdown | Assigned | Story Points (Hours) 1sp:1hr | Complexity | Start Date | Due Date (Internal) | Due Date (External) | Status | Comments
Product Proposal | Product Proposal - Implement Feedback 1 | Jack | 2 | Low | 2023-09-30 | ASAP | ASAP | In Progress | Work is tenative on professor feedback, major details already in doc
| Product Proposal - Implement Feedback 2 | Yoshiki | 2 | Low | 2023-09-30 | ASAP | ASAP | In Progress | See above
| Product Proposal - Implement Feedback 3 | Devin | 2 | Low | 2023-09-30 | ASAP | ASAP | In Progress | See above
| Product Proposal - Implement Feedback 4 | Zarif | 2 | Low | 2023-09-30 | ASAP | ASAP | In Progress | See above
| Product Proposal - Implement Feedback 5 | Phong | 2 | Low | 2023-09-30 | ASAP | ASAP | In Progress | See above
BRD | Non Features Requirements (User Types, Scope) | Devin | 7 | High | 2023-09-30 | 2023-10-10 | 2023-10-11 | In Progress | Our project proposal scope is close to BRD's/User Types need work
| BRD Phase 1 - 3 Features | Yoshiki | 13 | High | 2023-09-30 | 2023-10-10 | 2023-10-11 | In Progress
| BRD Phase 1 - 3 Features | Phong | 13 | High | 2023-09-30 | 2023-10-10 | 2023-10-11 | In Progress
| BRD Phase 1 - 3 Features | Jack | 13 | High | 2023-09-30 | 2023-10-10 | 2023-10-11 | In Progress
| BRD Phase 1 - 3 Features | Devin | 13 | High | 2023-09-30 | 2023-10-10 | 2023-10-11 | In Progress
| BRD Phase 2 Features | Zarif | 13 | Medium | 2023-09-30 | 2023-10-10 | 2023-10-11 | In Progress | Phase 2 features are low priority, phase 1 should be done first
| Glossary | Zarif | 5 | Low | 2023-09-30 | 2023-10-10 | 2023-10-11 | In Progress
Task Breakdown Comments
Product Proposal | Restructured to indicate actual team structure - when feedback comes we all do it quickly
BRD | Break down BRD to different section based on predicted difficulty and hours needed
Story Point assignment method | Used Party Poker during our task breakdown to estimate story points
For burndown charts - need to figure out how to implement the breaks/gaps in our chart for days not worked