## Sheet1
Date | Names | What did you do? | What will you do? | Blocked? | Comments?
2023-09-22 | Yoshiki | Sprint start | Product Proposal High Complexity Features
| Phong | Sprint start | BRD High Complexity Features
| Jack (SM) | Sprint start | Product Proposal Low-Medium Complexity Features
| Devin | Sprint start | BRD Scope, BRD Medium Complexity Features
| Zarif | Sprint start | BRD Glossary
2023-09-23 | Yoshiki | Worked on the product proposal's high complexity features | Environment Setup
| Phong | Product Proposal High Complexity Features | Environment Setup
| Jack | Product Proposal Low-Medium Complexity Features | Environment Setup |  | Submitting proposal tonight, while waiting for feedback setup enviorment
| Devin | BRD Scope, BRD Medium Complexity Features | Environment Setup
| Zarif | BRD Glossary | Environment Setup
2023-09-24 | Yoshiki | Completed Environement Setup | Work on BRD feature templates
| Phong | Completed Environement Setup | Work on BRD high complexity features
| Jack | Completed Environement Setup | Product Proposal Low-Medium Complexity Features |  | Expecting feedback tonight 9/24
| Devin | Completed Environement Setup | Work on BRD Scope, BRD Medium Complexity Features
| Zarif | Completed Environment Setup | Work on BRD Glossary
2023-09-25 | Yoshiki
Phong
Jack
Devin
Zarif
2023-09-26 | Yoshiki
Phong
Jack
Devin
Zarif